WBS Table / Project Plan – Timeline

Team Triple Threat

This table covers the project timeline for the planning, analysis, design and development, and the testing and full release of the Blackjack game.

| WBS ID | Task Name | Description | Predecessor | Duration | Resources |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Project Plan | Define project scope and goals | n/a | 1st week | Team Triple Threat |
| 1.1 | Requirements Gathering | Identify game features and rules | 1.0 | 1st week | Team Triple Threat |
| 1.2 | System Requirements or Feasibility Review | Check that we have the proper tools, skills, language, and resources | 1.1 | 1st week | Team Triple Threat |
| 2.0 | Game Design | Plan structure and appearance of game | 1.0-1.2 | 2nd – 5th week | Team Triple Threat |
| 2.1 | Game Rules Design | Define Blackjack rules and scoring | 2.0 | 2nd – 5th week | Team Triple Threat |
| 2.2 | Interface Design | Sketch layout (buttons, cards, score display) | 2.1 | 2nd – 5th week | Team Triple Threat |
| 2.3 | Game Flow Design | Plan how the game runs (from early play to mid game to end game). What does it look like to win? To lose? | 2.2 | 2nd – 5th week | Team Triple Threat |
| 3.0 | Development | Build the game system | 1.0-2.3 | 6th – 10th week | Team Triple Threat |
| 3.1 | Project Setup | Create project files and folders | 3.0 | 6th – 10th week | Team Triple Threat |
| 3.2 | Card & Deck System | Create card deck and shuffle logic | 3.1 | 6th – 10th week | Team Triple Threat |
| 3.3 | Player Logic | Handle player actions (Hit, Stand) | 3.2 | 6th – 10th week | Team Triple Threat |
| 3.4 | Dealer Logic | Program dealer behavior | 3.3 | 6th – 10th week | Team Triple Threat |
| 3.5 | Scoring System | Calculate hand values | 3.4 | 6th – 10th week | Team Triple Threat |
| 3.6 | UI Implementation | Build buttons, labels, and card display | 3.5 | 6th – 10th week | Team Triple Threat |
| 4.0 | Testing & Debugging | Verify game works correctly | 1.0-3.6 | 10th – 15th week | Team Triple Threat |
| 4.1 | Unit Testing | Test individual features | 4.0 | 10th – 15th week | Team Triple Threat |
| 4.2 | Gameplay Testing | Play full games to find errors | 4.1 | 10th – 15th week | Team Triple Threat |
| 4.3 | User Acceptance Testing | Find players to try and break the game and report errors. | 4.2 | 10th – 15th week | Team Triple Threat |
| 4.4 | Bug Fixing | Correct reported issues | 4.1-4.2 | 10th – 15th week | Team Triple Threat |
| 5.0 | Documentation & Delivery | Prepare final submission | 1.0-4.3 | 16th week | Team Triple Threat |
| 5.1 | User Guide | Write instructions for players | 5.0 | 16th week | Team Triple Threat |
| 5.2 | Technical Documentation | Describe code structure | 5.1 | 16th week | Team Triple Threat |
| 5.3 | Final Presentation | Prepare prototype demo/screenshots/video | 5.2 | 16th week | Team Triple Threat |
| 5.4 | Submission | Package and submit project | 5.3 | 16th week | Team Triple Threat |